## Stakeholder Map
Sample Stakeholder Map
Stakeholder | Source | Rationale (if inferred) | Department/Group | Role in Project | Influence Level | Interest Level | Engagement Strategy | Key Concerns | Communication Frequency | Engagement Approach | Communication Method
Deloitte Client Representatives | Explicit | N/A | Client / Consulting | Provide project expectations, evaluation criteria, and feedback | High | High | Manage Closely | Quality of outputs, professionalism, usefulness of agent | Weekly | Progress reviews, milestone sign-offs, feedback sessions | Meetings, presentations, email
Project Team Lead | Explicit | N/A | Student Team | Oversees coordination, deadlines, and team integration | High | High | Manage Closely | Timeline management, team alignment, project completion | 2–3 times per week | Team coordination, issue resolution, task tracking | Team meetings, chat
AI Developers | Inferred | AI agent development is required to build and implement the proposed solution | Technical Team | Build and implement the AI agent and revision loop | High | High | Manage Closely | Technical feasibility, integration, prompt reliability | 2–3 times per week | Technical reviews, sprint planning, testing discussions | Team meetings, shared docs
Stakeholder Management Analyst | Explicit | N/A | Consulting / Operations | Designs stakeholder mapping template and stakeholder logic | Medium | High | Keep Informed | Accuracy of stakeholder identification and communication structure | Weekly | Stakeholder review sessions and feedback incorporation | Shared docs, meetings
RAID Analyst | Inferred | Risk identification and management are required deliverables within the project scope | Consulting / Operations | Develops RAID framework and risk identification structure | Medium | High | Keep Informed | Completeness of risks, dependencies, and mitigation plans | Weekly | Risk review discussions and coordination with workstream leads | Meetings, collaborative docs
QA / Testing Members | Explicit | N/A | Quality Assurance | Test outputs, identify errors, and validate deliverables | Medium | High | Keep Informed | Reliability, consistency, and usability of outputs | Weekly | Testing reviews, issue reporting, validation feedback | Shared trackers, meetings
End Users / Evaluators | Explicit | N/A | Academic / Client Reviewers | Review and evaluate final project deliverables | High | Medium | Keep Satisfied | Clarity, usability, and professionalism | At major milestones | Demonstrations and feedback collection | Demo presentations
Course Instructors / TAs | Explicit | N/A | Academic | Assess project quality and assignment requirements | High | Medium | Keep Satisfied | Assignment alignment and learning outcomes | As needed | Milestone reviews and clarification discussions | Email, office hours