## RAID Log - Detail
| RAID Log | [5 empty] | Date Created:
Project name
Risks | [11 empty] | Actions | [6 empty] | Issues | [5 empty] | Decisions
ID No. | Title | Description | Status | Mitigation | Owner | WBS Links | Probability | Impact | Risk Rating | Risk Appetite | Priority | ID No. | Title | Description | Status | Owner | WBS Links | Priority | ID No. | Title | Description | Resolution | Owner | Priority | ID No. | Title | Description/Justification | Resolution | Owner | Priority
R1 | [6 empty] | High | Moderate | High | Moderate | Monitor closely | A1 | [5 empty] | High | I1 |  |  |  |  | High | D1 |  |  |  |  | High
R2 | [6 empty] | Moderate | Low | Moderate | Moderate | Monitor | A2 | [5 empty] | Moderate | I2 |  |  |  |  | Moderate | D2 |  |  |  |  | Moderate
R3 | [6 empty] | Low | High | Moderate | Moderate | Stay informed | A3 | [5 empty] | Low | I3 |  |  |  |  | Low | D3 |  |  |  |  | Low
R4 | [6 empty] | Low | Moderate | Moderate | Moderate | Stay informed | A4 | [5 empty] | Low | I4 |  |  |  |  | Low | D4 |  |  |  |  | Low
R5 | [6 empty] | Very Low | Very low | Low | Moderate | Respond as required | A5 | [5 empty] | High | I5 |  |  |  |  | High | D5 |  |  |  |  | High
R6 | [6 empty] | Moderate | very high | High | Moderate | Monitor | A6 | [5 empty] | Moderate | I6 |  |  |  |  | Moderate | D6 |  |  |  |  | Moderate
Risk Rating
|  |  |  | Probability | Impact
| Probability | Numerical rating
| very low | 1 in 150,000, less then 0.001% |  |  | very low | low | moderate | high | very high
| low | 1 in 15,000, less then 0.01% |  | very low | Very Low | Low | Low | Moderate | High
| moderate | 1 in 80, 1.25% |  | low | Low | Low | Moderate | Moderate | High
| high | 1 in 8, 12.5 % |  | moderate | Low | Moderate | Moderate | High | High
| very high | 1 in 3 and greater, 33+% |  | high | Moderate | Moderate | High | High | Very High
|  |  |  | very high | High | High | High | Very High | Very High
Institutional risk management planning, monitoring and reporting requirements
|  |  |  | Risk Appetite | Risk Rating | Required Action
|  |  |  | High, Moderate, Low | Very High | Monitor closely: Ensure the project's sponsor or governace is aware of risk and agrees with the plan to manage risk. If the risk has an institutional impact, ensure this is communicated so that the risk can be further escalated. In addition, speak to your director about the escalation plan to track and keep abreast of decisions that may affect the project.
|  |  |  | Moderate, Low | High | Monitor: Ensure the project's sponsor or governance is aware of risk and agrees with the plan to manage risk. If the risk has an institutional impact, ensure this is communicated so that the risk can be further escalated. Track when the risk is escalated.
|  |  |  | Low, moderate | Medium | Stay informed: Report the risk up to the project’s sponsor or governance team to determine if the management plan for the risk is acceptable.
|  |  |  | N/A | Low - Very Low | Respond as required: Requires no attention above routine practices and procedures, and monitoring.